## Slide 1: Compliance Review For Project Administrators
Carlos M Rodríguez Rivera - Director
Office for Research Compliance & Integrity
University of Puerto Rico

## Slide 2: Rules
Phone calls should be answered outside. Texts are OK.
Questions related to a topic may be asked anytime.
Specific questions related to a particular situation may be raised individually at the end of the presentation.
Training materials will be made available to you,

## Slide 3: Objectives for today
Understand the scope of this presentation
Understand the requirements and nuisances involved in maintaining compliance throughout a grant cycle
Outline the goals, best practices and common pitfalls in maintaining compliance
Be better prepared to administer a grant effectively

## Slide 4: Scope
The topics for today will be limited to administrative requirements only
Programmatic or regulatory compliance is topic for another training

## Slide 5: What is compliance?
Webster:
“the act or process of complying to a desire, demand, proposal, or regimen or to coercion.”

## Slide 6: Compliance Requirements… Why?
Grantor Perspective
Stewardship of funds
Minimize risks
Eliminate misuse
Maximize tax dollars
Ensure progress
Grantee Perspective
Improve chances for future funding cycle
Focus on objectives
Efficiency
Ethics

## Slide 7: Which Requirements?
Award Terms & conditions
Particular Agency General Guidelines, Policies & Regulations
General Guidelines (OMB 2 CFR 200, etc. )
Program Guidelines
Statutory requirements
The Law
Institutional Policies
Follow the most restrictive

## Slide 8: Grant Cycle
Idea
Locate Funding
Proposal
Submittal
Closeout
Project Setup
Project Execution
Negotiation

## Slide 9: Grant Administrators
What you should be:
Facilitator
Liaison between project and Institutional Offices
Steward of projects
Coordinator
Counterweight
What you should not be:
Project PI
Accountant
Bypass Mechanism
Scapegoat
Grant Admin
_____________ Fill the blank

## Slide 10: Who is responsible?
At the Institution
PI (by extension Grant Admins)
Authorized Organizational Representative
Institutional Officials
At the Agency
Grants Management Officer / Specialist
Program Officer
Scientific Reviewer

## Slide 11: Ground Rules
You must comply with all Federal and Institutional policies, guidelines and regulations.
Read the NOA and be aware of the award terms & conditions
Institutional policies might be more restrictive. Be aware.
Grants are awarded to the Institution
By drawing funds you agree to comply with all applicable regulations

## Slide 12: Grant Admin’s best practices to guarantee compliance
Establish written roles & responsibilities within your projects and agree on a management plan with your PIs.
Tie your admin plan to your PI’s project execution plan.
Foster kickoff meetings to discuss what actions are required to accomplish project objectives and establish who, when and how those actions should be performed.

## Slide 13
COMMUNICATE. Encourage regular meetings with project staff and institutional officials. Follow-up and escalate issues as appropriate.
DOCUMENT!!! In Writing!!!
REVIEW. Make sure your award file is complete on a regular basis.
Train your people
Grant Admin’s best practices to guarantee compliance (cont.)

## Slide 14: It’s about the money… So, you should understand the language.
Familiarize with the policies, procedures and challenges at the different stages of the accounting and administration process.
Make sure you understand the project’s budget and how it is tied with the project’s objectives.
Understand your institution’s documentation.
Understand the Chart of Account.

## Slide 15: Account Structure
Fund
Dpt
Sub-Dpt
Object Code
Function
Project #
Fiscal Year
XXXXX.XXX.XXX.XXXX.XXX.XXXXXXXXXXXX.XX

## Slide 16: Account Structure - Fund
Fund– Establishes financing source (five numeric characters)
  First 2 characters identify the institutional Unit.
  Remaining 3 characters identify the source.
  ie. 10231
    10 – Central Administration
    231 – Direct Federal Project / Collaborative agreements

## Slide 17: Account Structure – Object Code
Established by 4 numeric characters that identify assets, liabilities, fund balances, income or expenses.
  6000 – 6057 Materials
  6080 – 6083 Parts for equipment repairs
  6100 – 6122 Mainteinance costs
  7000 – 7499 Equipment
  7600 – 7699 Capital Equipment

## Slide 18: Account Structure – Project
Project Number – 12 alphanumeric characters (in federal accounts: only numeric characters).
  1,2 – Unit
  3,4,5 – Agency
  6,7,8,9,10 – Project identifier
  11,12 – Budget year

## Slide 19: 2 CFR 200: Uniform administrative requirements, cost principles, and audit requirements for federal awards
Subpart A—Acronyms and Definitions
Subpart B—General Provisions
Subpart C—Pre-Federal Award Requirements and Contents of Federal Awards
Subpart D—Post Federal Award Requirements
Subpart E—Cost Principles
Subpart F—Audit Requirements
Notes: Estas son las subparts de las guias
Nos enfocaremos en los principios de costos y las definiciones

## Slide 20: Basic Concepts Required to understand cost principles
Reasonableness
Allocability
Conformance
Direct Cost
Indirect Cost
Allowability
MUST = REQUIRED
SHOULD = Best practice or recommended
Notes: Para poder dilucidar la permisibilidad de costos, hay que entender estos conceptos basicos.

## Slide 21: Reasonableness
§200.404 - Reasonable costs
A cost is reasonable if, in its nature and amount, it does not exceed that which would be incurred by a prudent person under the circumstances prevailing at the time the decision was made to incur the cost.
Ordinary and necessary for the operation of the non-Federal entity or the proper and efficient performance of the Federal award.
Notes: Costo no exceed lo que haria una persona prudente en circunstancias similares
Ordinario y necesario para el desempeño del award.
Quien es prudente? Verificar decisiones pasadas, consultar, verificar politica institucional, auditorias.

## Slide 22: Reasonableness (cont)
Requirements
  sound business practices
  arm's-length bargaining
  Follow federal, state, local, tribal, and other laws and regulations
  Follow terms and conditions of the Federal award
  Market prices for comparable goods or services for the geographic area
  Prudence
  Evaluate deviations from established practices and policies
Notes: Practicas robustas de negocio
No estar en la cama con el suplidor – conflicto de interes.

## Slide 23: Allocability
§200.405 Allocable costs.
A cost is allocable to a particular Federal award or other cost objective if the goods or services involved are chargeable or assignable to that Federal award or cost objective in accordance with relative benefits received.

## Slide 24: Allocability (cont)
Tests for allocability:
Is incurred specifically for the Federal award
Cost benefits both sponsored agreement & other work in proportions that can be approximated by reasonable methods
Is necessary to the overall operation of institution and is deemed to be assignable in part to sponsored projects
No shifting of costs from one fund to another to cover cost overruns, avoid restrictions on agreement or for reasons of convenience

## Slide 25: Conformance
Test for allowability-conformance deals with limitations and exclusions as contained in the terms and conditions of award, including those in the cost principles varies by the type of activity, the type of recipient, and other characteristics of individual awards.

## Slide 26: Direct
§200.413 Direct costs.
Can be identified specifically with a particular final cost objective, such as a Federal award, or other internally or externally funded activity, or that
Can be directly assigned to such activities relatively easily with a high degree of accuracy

## Slide 27: Indirect (F&A)
§200.56 Indirect (F&A) costs
Indirect (F&A) costs means those costs incurred for a common or joint purpose benefiting more than one cost objective,
Not readily assignable to the cost objectives specifically benefitted,
Indirect (F&A) cost pools must be distributed to benefitted cost objectives on bases that will produce an equitable result in consideration of relative benefits derived.

## Slide 28: Direct or Indirect (F&A)
§200.412 Classification of costs.
There is no universal rule for classifying certain costs as either direct or indirect (F&A)
A cost may be direct with respect to some specific service or function, but indirect with respect to the Federal award or other final cost objective.

## Slide 29: Direct or Indirect (F&A)(Cont.)
Item of cost incurred for the same purpose be treated consistently in like circumstances either as a direct or an indirect (F&A)
Context is important

## Slide 30: Direct or Indirect Costs
Direct | Indirect
Materials and Supplies: Scientific Materials or materials directly related with project objectives. | Office Materials: Paper, pens, toner, chairs, other.
Equipment: Equipment for scientific or specialized use with an acquisition cost over $5,000 and a useful life above 1 year. | Equipment: Office general equipment like Xerox machines, etc.
Computing Devices: When essential and allocable to the execution of a project. | Computing Devices: Desktop Computers, printers, external drives, scanners, laptops, etc.
Facilities: Rent to third parties of spaces classified as off-campus dedicated exclusively to a project. (note this will force an off-campus indirect rate). | Facilities: Utilities, buildings, maintenance, renovations, etc.

## Slide 31: Direct / Indirect Decision Tree
Does the cost result in a direct benefit to the grant?
Is it necessary to the overall operation of the organization?
Rethink whether the cost is allowable
Can it can be easily and accurately traced to the grant?
Does it benefit more than 1 grant?
Is it normally charged as indirect?
Have you calculated proportional benefit?
Indirect
DIRECT
Indirect
Calculate proportional benefit
DIRECT
NO
YES
YES
YES
NO
YES
NO
NO
NO
YES
NO
YES

## Slide 32: Allowability
200.403 Factors affecting allowability of costs. Except where otherwise authorized by statute, costs must meet the following general criteria in order to be allowable under Federal awards:
Conform to any limitations or exclusions
Consistent treatment between direct and indirect costs
GAAP (except governments)
Cannot be used as cost share
Be adequately documented
Necessary, Reasonable and Allocable
Be consistent with policies and procedures that apply uniformly to both federally-financed and other activities of the non-Federal entity

## Slide 33: Allowability direct vs indirect
§200.403 Factors affecting allowability of costs.
"(d) A cost may not be assigned to a Federal award as a direct cost if any other cost incurred for the same purpose in like circumstances has been allocated to the Federal award as an indirect cost."

## Slide 34: Determining Allowability
Procurement Decision-Making Process
REASONABLE
Approved Grant Budget
Project Description
NECESSARY / CONFORM
Grant Objectives
Financial / Inventory Records
ALLOCABLE
If equipment A is listed on:
If equipment A has gone through the:
If equipment A has links to the grant Project in the:
ALLOWABLE
If equipment A is: NECESSARY, REASONABLE,ALLOCABLE and CONFORMS grant term & condition then it is:

## Slide 35: All conditions for allowability must be met.
A cost allocable to an award is not necessarily reasonable
  Example: Buy a sport car to transport food
A reasonable cost may not be allocable to an award
  Example: The purchase of a Xerox machine
A cost may be reasonable and allocable but does not conforms to award terms and conditions or defined as unallowed in the regulation
  Example: Lobbying costs

## Slide 36: -Oh, but is budgeted, therefore allowed! -Well… it doesn’t matter.

## Slide 37: Agencies’ stance on allowability
NIH Grants Policy Statement: “The fact that a proposed cost is awarded as requested by an applicant does not indicate a determination of allowability.” https://grants.nih.gov/grants/policy/nihgps/HTML5/section_7/7.2_the_cost_principles.htm
NSF Award and Administration Guide:
It is the grantee organization that is ultimately responsible for ensuring that all costs charged to NSF awards meet the requirements of the cost principles contained in 2 CFR § 200, Subpart E, grant terms and conditions, and any other specific requirements... http://www.nsf.gov/pubs/policydocs/pappguide/nsf16001/aag_5.jsp

## Slide 38: Cost Principles Applicability
The applicable costs principles for an organization are determined by the type of the organization
Sub-recipients do not grandfather cost principles applicability
Example: A for-profit institution entered in an award as a sub-awardee with an Institution of Higher Education. Although the prime awardee is governed by the 2 CFR 200 the for-profit institution has to comply with 48 CFR 31.2.

## Slide 39: Cost Principles Applicability
Type of Organization | Applicable Cost Principles Regulation
College or University | 2 CFR 200
State, Local, or Indian Tribal Government | 
Nonprofit Organization | 

## Slide 40: Cost Principles Applicability
Type of Organization | Applicable Cost Principles Regulation
Profitmaking Organization | 48 CFR 31.2
Hospital | Cost principles used by awarding agency, usually 45 CFR 75, Appendix IX

## Slide 41: Selected Items of Costs (§200.420-§200.475)
Establishes the allowability of specific cost items.
Establishes guides on the allocation of costs (direct vs indirect)
If a cost is not found on this list, it does not means that is allowable or unallowable. Judgement should be exerted using similar or related items of cost
In case of a discrepancy between the provisions of a specific Federal award and the provisions in the items of costs, the Federal award governs (hint: more restrictive prevails)

## Slide 42: Selected Items of Costs - Materials & Supplies (§200.453)
Cost for materials, supplies, computing devices and fabricated parts necessary to carry out a Federal award are ALLOWABLE
Must be charged at their actual prices, net applicable credits.
Incoming transportation charges are a proper part of materials and supplies costs
Charged as direct cost

## Slide 43: Selected Items of Costs - Materials & Supplies (§200.453)
Example:
Item of Cost - Costs of paper examination gowns for a mobile clinic serving migrant worker populations | 
Allowability | Allowable
Direct / Indirect | Direct
Citation in 2 CFR 200 | 200.453

## Slide 44: Purchases: Uniform Guidance Procurement Claw
Micro Purchase
Up to $3,500.00
No Quotes
UPR – $3,000
Small Purchases
Up to $150,000.00
Reasonable # of quotes
UPR - $50,000 ($150,000)
Sealed Bids
Over $150,000.00
Price is the most important factor
Competitive Proposal
Over $150,000.00
RFP with evaluation methods
Sole source
Emergency
No competition
Justify

## Slide 45: Purchases: Applicable Institutional Policies
Certificación 30 2008-2009 (DRAFT)
  Art. 15.A.2 - En compras donde el precio sea igual o mayor de tres mil dólares ($3,000) por transacción, pero menor de ciento cincuenta mil dólares ($150,000) en total, se solicitarán no menos de tres (3) cotizaciones por escrito (ya sea en original, facsímile, correo electrónico, por internet u otro medio adecuado para este propósito).

## Slide 46
Circular 14-18 (Ammended), June 18th, 2014 – Equipment Capitalization threshold change
Circular 14-19, June 25th, 2014 – Object Codes to account for Circular 14-18
Circular 15-01, July 7th, 2014 – Object Codes for shipment and installation of Capital Equipments
Purchases: Applicable Institutional Policies

## Slide 47
Credit Cards
Circular de Finanzas 15-25 – Procedimiento uso de tarjeta de crédito
Circular de Finanzas 16-02 (Ammended) – Increase the monthly limit from $3,000 to $20,000 to PI’s with grants budgets above $1,000,000.
Purchases: Applicable Institutional Policies

## Slide 48
Circular ORCI 17-02 – Periodos Límites de Adquisiciones Cargadas a Proyectos Federales
  Internal control measures included in this circular are applicable only to final project closeout.
  90 days before the period of performance end, purchases will not be allowed unless:
    Approved no-cost extension
    Capital Equipment - Sponsored Agency prior approval
    Materials and non-capital equipment – Justification letter
Purchases: Applicable Institutional Policies

## Slide 49: Purchases: Equipment vs Materials
$5,000.00
Equipment
Materials
FEDERAL
UPR
$5,000.00
$1,000.00
Capital Equipment
Equipment
Materials
Computers
$500.00

## Slide 50: Purchases: What is your role as Grant Admin
Coordinate the purchases with enough time as to not affect project execution. Establish a purchasing plan.
Document decision making process.
Facilitate quotes and specifications. However, remember that is the responsibility of the purchasing officer to complete the process, which may include the request of additional quotes independently or to request additional information from the PI/Grant Admin.
Notify the delivery of goods to the corresponding officer.
Keep a project inventory of goods.
Follow-up

## Slide 51: An approved budget is not a “Carte blanche”
When making spending decisions:
  Analyze the context of the expense. A cost deemed allowable at budget preparation might change at the time of the expense.
  Make sure you do test for allowability at the time of the expense (necessary, reasonable, allocable).
  Evaluate less expensive alternatives as market conditions change.
  Document!

## Slide 52: Cost Justification Documentation
Whenever the allowability is not clear, you should do the following before taking the decision and keep documentation for each case:
Document the rationale for your decision. Describe your process on how you concluded a cost is allowable. If you are not able to write this concisely and logically, probably you should not go forward with the cost.
Document prior approvals.
Make sure the regulations and/or terms & conditions do not contradict your decision.
Research and document existing cases (internal and external)

## Slide 53: Prior Approvals
Although, some actions are allowable under 2CFR200, some of them require prior approval or allow agencies to opt-out on prior approval requirements .
Federal Demonstration Partnership Prior Approval Matrix provides an overview of different actions along their prior approval requirements:
https://www.nsf.gov/bfa/dias/policy/fedrtc/appendix_a.pdf
Example:
Item | Reference | RTC Overlay | NSF | DOE | NIH
Transfer amounts budgeted for indirect costs to absorb increases in direct costs, or vice versa. | 200.308(d)(4) | Waived | Waived | Waived | Waived – Unless it changes scope

## Slide 54: Cost Share or Matching
200.336 - Cost sharing or Matching:
Verifiable in the institution’s records (separate account)
Not included in any other project
Necessary and reasonable to accomplish Objectives
Allowable
Approved by the Agency

## Slide 55: Cost Share or Matching
Caveats
Once the NOA is received, the Institution agrees to the dollar amount established in it, not the proportion between federal and cost shared dollars.
Cost shared dollars are to be treated as federal dollars. All federal regulations are applicable.
Cost Shared expenses also generate indirect (F&A) costs which may be included in the cost sharing.
Unrecovered indirect costs may be cost shared with agency prior approval.

## Slide 56: Identify sub-recipients correctly
SUBRECIPIENT 200.330(a) | CONTRACTOR / VENDOR
Determines who is eligible to participate in a federal program | Provides the goods and services within normal business operations
Has its performance measured against whether the objectives of the federal program are met | Provides similar goods and services to many different purchasers
Is responsible for programmatic decision making | Operates in a competitive environment
Is responsible for complying with federal program requirements | Provides goods or services that are ancillary to the operation of the federal program
Uses the federal funds to carry out a program | Is not subject to the compliance requirements of the federal program as a result of the agreement
Notes:   Uses the federal funds to carry out a program as compared to providing goods or services for a program of the pass-through entity.
  Circular del president R-1213-3A 14 de mayo de 2013

## Slide 57: Subrecipient Risk Monitoring Background
Regarding risk monitoring of subawards, the 2 CFR 200, section 200.331 (6)(b) indicates the following need: “Evaluate each subrecipient’s risk of noncompliance with Federal statutes, regulations, and the terms and conditions of the subaward for purposes of determining the appropriate subrecipient monitoring described in paragraph (e) of this section, which may include consideration of such factors as...”
Notes: Decidir como se van a manejar los proyectos multianuales con subrecipientes
(6) Appropriate terms and conditions concerning closeout of the subaward.
(b) Evaluate each subrecipient's risk of noncompliance with Federal statutes, regulations, and the terms and conditions of the subaward for purposes of determining the appropriate subrecipient monitoring described in paragraphs (d) and (e) of this section, which may include consideration of such factors as:
(1) The subrecipient's prior experience with the same or similar subawards;
(2) The results of previous audits including whether or not the subrecipient receives a Single Audit in accordance with Subpart F—Audit Requirements of this part, and the extent to which the same or similar subaward has been audited as a major program;
(3) Whether the subrecipient has new personnel or new or substantially changed systems; and
(4) The extent and results of Federal awarding agency monitoring (e.g., if the subrecipient also receives Federal awards directly from a Federal awarding agency).

## Slide 58: Subrecipient Risk Monitoring Background
200.331(6)(e), “Depending upon the pass-through entity’s assessment of risk posed by the subrecipient (as described in paragraph (b) of this section), the following monitoring tools may be useful for the pass-through entity to ensure proper accountability and compliance with program requirements and achievement of performance goals... “.
  Providing subrecipients with training and technical assistance
  Performing on-site reviews

## Slide 59: Subrecipient Risk Monitoring Background
200.331(h), Pass-through entities must consider taking enforcement action based on noncompliance, including:
  Temporarily withholding cash payments pending correction
  Disallowing all or part of the cost
  Wholly or partly suspending the award
  Recommending suspension/debarment to federal awarding agency
  Withholding further federal awards
  Other remedies that may be legally available

## Slide 60: Subrecipient Monitoring Guide
Serial ORCI-2016-01- University Of Puerto Rico Risk Management Procedures For Federal Grants Subawards (July 2016) http://www.upr.edu/wp-content/uploads/2017/04/SERIAL-ORCI-2016-01-UNIVERSITY-OF-PUERTO-RICO-RISK-MANAGEMENT-PROCEDURES-FOR-FEDERAL-GRANTS-SUBAWARDS-JUL_18_2016-1.pdf
Designed for subawards that are subject to federal and/or agency-specific regulations established by the federal prime sponsor.
Monitoring procedures should be determined by the PI and administrators based on the nature of the grant and the perceived risk associated with the subrecipient.

## Slide 61: Subrecipient Monitoring Guide
Collection of documents to assist administrators at the responsible offices and central level with subrecipient monitoring.
Additional monitoring efforts should always be implemented if there is any question about the subrecipient’s ability to ensure proper use and financial management of sponsor funds during any stage of the award.

## Slide 62: Sub-Recipient monitoring
Finance Office circular 16-17
  http://www.upr.edu/wp-content/uploads/2017/04/Finance-Circular-16-07-Intecampus-Sub-Award-AMENDED.pdf
  Approved in september 28, 2015, amended on june 30, 2016.
  Differentiates the contract requirements of grants agreements between UPR units from grants agreements with external entities.
  Defines the accounting for grant agreements between UPR units.
  Establishes the “Intercampus Subaward Agreement” as the official UPR document to be used to formalized grants agreements between UPR units.
Notes: Base legal para llegar a esta circular: El documento es creado partiendo de la base de que la UPR reporta un solo single audit y cualquier señalamiento federal de acciones de parte de cualquiera de las unidades de la UPR tendrá que ser reportada solo bajo una UPR. Ejemplo……
- Create the accounting fund 236 to be used to identified on the accounting system grants agreements between UPR units.
Componentes:
Agreements Units
Grant Info: Agency, Name of Award, Award Number, CFDA Number
Intercampus subaward info: Amount, Period, Scope of Work
Comments: Billing terms, etc.
Attachments; grant agreement, detail Budget, etc.
Certification: Chancellor from the Intercampus
NOTE: Un subaward con otra unidad UPR que se hubiera hecho un contrato antes de la fecha de septiembre 28, 2015 no se utilizara el nuevo documento hasta la fecha de vencimiento del contrato.

## Slide 63: Participant Support Costs
Individual Budget line in awards and reporting – make sure to track accordingly.
Prior approval is required to include or make changes to this budget line
Selection criteria for participants must be documented and clearly stated in writing
Term & Conditions may exclude Participant Support Costs from F&A calculations
Make sure to read the fine print on your award regarding Participant Support

## Slide 64: Closeout: 2 CFR 200.343 – Closeout
  “…all applicable administrative actions and all required work of the Federal award have been completed by the non-Federal entity…”.
  no later than 90 calendar days after the end date of the period of performance, all financial, performance, and other reports
  must liquidate all obligations
  prompt payments to the non-Federal entity for allowable reimbursable costs
  (non-federal entity) must refund any balances of unobligated cash
  agency or pass-through entity must make a settlement for any upward or downward adjustments
  must account for any real and personal property acquired
  agency or pass-through entity should complete all closeout actions for Federal awards no later than one year after receipt and acceptance of all required final reports.

## Slide 65: Goals of a Closeout
All involved parties agree that:
  All work has been completed
  Fiscal matters have been settled
  Deliverables are submitted and accepted
  Compliance matters are in place
  All administrative actions are finished

## Slide 66: Bilateral vs Unilateral Closeout
Bilateral Closeout
Bilateral closeout is closeout with the cooperation of the recipient and the funding agency.
All parties are in agreement
Unilateral Closeout
Unilateral closeout is the process by which the funding agency closes out an award without receipt of acceptable final reports required by the terms and conditions of an award, after making reasonable efforts to obtain them. It is a measure of last resort.
Timeliness is extremely important to avoid a unilateral closeout

## Slide 67: Understanding Closeout Requirements
Before 90 (120 NIH) calendar days from stated project end date in the NOA:
Final Financial Report
Performance / Technical Final Report
Terms & Conditions Deliverables
Property Reports
Liquidate Obligated Balances

## Slide 68: What are the alternatives for unforeseen issues at closeout?
The UG does not provide remedies
However, communicate with your program officer or agency to request an extension
Most agencies do have policies on closeout extensions

## Slide 69: Questions

## Slide 70: References
PART 200—UNIFORM ADMINISTRATIVE REQUIREMENTS, COST PRINCIPLES, AND AUDIT REQUIREMENTS FOR FEDERAL AWARDS, http://www.ecfr.gov/cgi-bin/text-idx?tpl=/ecfrbrowse/Title02/2cfr200_main_02.tpl
Management Concepts - Advanced Cost Principles - Avoiding Problem Areas & Responding to Questioned Cost Student Guide
Management Concept - Uniform Administrative Requirements for Federal Grants: 2 CFR 200 (Subparts A through D) Student Guide
Management Concept - Cost Principles for Federal Grants 2 CFR PART 200 (SUBPART E) AND FAR 31.2 Student Guide
Management Concepts - Developing & Monitoring Indirect/F&A Cost Rate Proposal Student Guide
Uniform Guidance - How does this affect my Grant?, Jason Galloway, Associate Controller HSC Contract and Grant Accounting
Rensselaer Research Administration & Finance:Uniform Guidance Cost Principles Reference Guide, https://www.rpi.edu/dept/finance/docs/research/UGCostPrinciplesReferenceGuide.pdf
NSF Award and Administration Guide, http://www.nsf.gov/pubs/policydocs/pappguide/nsf16001/aag_index.jsp
NIH Grants Policy Statement, http://grants.nih.gov/policy/nihgps/index.htm